## Plan for Regression test
PROJECT NAME | ( Sprint -1 )Testing automation – Flutter App ( Regression test)
PROJECT DELIVERABLE | Set of scripts related automation testing using flutter driver
SCOPE STATEMENT | Build script for Mobile [IOS , Android] and web Web
START DATE |  | END DATE |  | OVERALL PROGRESS | 10%
SPRINT 1 | TASK | Status | START | END | Duration | Commemnts
|  |  | DATE | DATE | in hours
Environment Prepration and System configuration | Install Java JDK (not less than java version "1.8.0_261") | Done | 28/3 | 28/3 | 16 Hours
| Install Windows PowerShell 5.0 | Done | 28/3 | 30/3
| Install JMeter | Done | 28/3 | 28/3
| Install Flutter SDK | Done | 28/3 | 28/3
| Update Flutter path (from environmental variable) | Done | 28/3 | 28/3
| Run flutter doctor | Done | 28/3 | 28/3
| Install Android Studio | Done | 30/3 | 30/3
| Enable flutter/Dart plugin in android studio | Done | 30/3 | 30/3
| Set up Android device(emulator) | Done | 30/3 | 30/3
| Web setup (install chrome driver, internet explorer driver) | Done | 30/3 | 30/3
Implementation (Build a test scripts) | Open and run existing flutter app (sorce code should contain Sprint 1 List of services ) and understand the flow | Done | 24/8 | 24/8 | 2 Hours
| Add flutter test dependencies in to yml file (flutter driver, CSV, screenshots, etc) | Done | 24/8 | 24/8 | 1 hour
| Create the test files: 1. Create folder with name “test_driver”. | Done | 24/8 | 24/8
| 2. Under (“test_driver”) folder, create Three folders with Below names: - “pages” - “Testcase” - “TestData”. | Done | 24/8 | 24/8
| 3. Under (“pages”) folder, create another folders with Below names: - “User Management” - “Dashboard” | Done
| 4. Build test scripts: for above folders each folder contains customize dart files as below : - User Management : 1. New user registration 2. Login 3. Forget Password 4. Forget UserName 5. Mobile Number Change - Dashboard : 1. My Favourites 2. RM Details 3. Investments 4. CB Notification and Announcements 5. View e statements/Download/Email 6. Share Iban 7. Share QR code 8. Copy IBAN Number 9. Digital Signed statement 10. Dashboard View 11. WhatsNew | My current build contains below services : what was done and working fine : 1. Login 2. Share IBAN 3. Share QR code 4. Copy IBAN 5. Dashboard View 6. Account transactions what was done and service result fail due to service issue once issue solve will get success result using same script : 1. Forget password 2. Forget username what are currentlly working on it : 1. My Favorites 2. CB Notification and annoucement |  |  | 30 Hours
Run the integration test | 1.Run program by select android channel for mobile app 2.Run program by select ios channel for mobile app 3. Using channel as RIB | Pending | _ | _ | 5 Hours
Check test result and Artefacts | 1. Review the excelsheet for having MOB test result 2. Review the excelsheet for having RIB test result 3. RIB and Mobile screenshots checkes | Pending | _ | _ | 10 Hours
Final review for Sprint 1 |  | Pending | _ | _ | _

## Plan -Load test
PROJECT NAME | ( Sprint -1 )Testing automation –Load test using jmeter
PROJECT DELIVERABLE | test report
SCOPE STATEMENT | Load test for services that developed using json request (RIB , MOB)
START DATE |  | END DATE |  | OVERALL PROGRESS | 10%
SPRINT 1 | TASK | Status | START | END | Duration | Commemnts
|  |  | DATE | DATE | in hours
Environment Prepration and System configuration | Install Java JDK (not less than java version "1.8.0_261") | Done | 2021-10-06 | 2021-10-06
| Download JMeter | Done | 2021-10-06 | 2021-10-06
| Enable Acheck the connectivity between server and My PC , inorder allow Jmeter to access the server via proxy | Done
| Enable proxy in Jmeter | Done | 13/6/2021 | 13/6/2021
| add Jmeter packages related sycronization | Done | 13/6/2021 | 13/6/2021
Implementation for Load test script (Sprint 1 services) | 1. Add Thread Group | Done
| 2. add Load test scripts: Gets the debit-able accounts. Gets the creditable accounts. Gets Account Transaction History by account number and date range. Gets the Customer accounts. Gets the WMS accounts. Gets the Alternatif accounts. Gets the Get Dynamic Popup. Gets Card Transaction History by card serial number and date range. Gets the customer cards. Authenticates the card by pin or CVV. Gets the country list. Gets the currency list. Gets the push notifications. Sends the e statement. Sends the validation otp. Get RM Details By Base Number. Get Digitally Signed Statement. Enquire Digitally Signed Statement. Get DigitallySigned Statement. Send Mail Request For IBAN Letter. Get Qid Expire Alert Message. Log the API gateway request and response details Authenticates the specified model. Regenerate the authentication token Logout the current user Get language text list Get all language text list Gets the exchange rate. Is CB Customer. Is Customer Registered With Mobile Banking. Validates the authentication code. Validates the user. Updates the password. Forgot the username. Registers the specified model. | Currentlly working for load test for transfer service using same user and transaction result in same mintes and second but still there is some time vaarriation tht need to be check , result attached on mail |  |  | 30 Hours
| Step 3) Adding Graph result | partially done
| Step 4) Run Test and get the test result | partially done
Final review for Sprint 1 |  | Pending |  |  | _